**3 Year Plan for Assessing DLOs**

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **DLOs** | **Fall 2017** | **Winter 2018** | **Spring 2018** | **Summer 2018** | **Fall 2018** | **Winter 2019** | **Spring 2019** | **Summer 2019** | **Fall 2019** | **Winter 2020** | **Spring 2020**  | **Summer 2020** | **Fall 2020** |
| **COM/IIT** | Finalize COM and IIT rubric; determine how work will be collected; craft e-mails for feedback on rubrics and for submission of work | Begin collecting work for COM and IIT | Continue collecting COM and IIT work, norm rubrics and begin scoring  |   | Continue collecting and scoring COM and IIT work | Finish scoring COM and IIT work and write report | Present final COM and IIT report to IASC and IC for endorsement |   |   |   |   |   | Begin collecting work for COM and IIT; norm rubrics; score work as it is submitted |
| **CRT/RES** |   |  | Finalize CRT and RES rubric |   | Begin collecting work for CRT and RES | Continue collecting CRT and RES work, norm rubrics and begin scoring | Continue collecting and scoring CRT and RES work  |   | Finish scoring CRT and RES work and write report | Present final CRT and RES report to IASC and IC for endorsement |   |   |   |
| **ICD/COK** |   |   |   |   |  | Finalize ICD and COK rubric | Begin collecting work for ICD and COK |   | Continue collecting ICD and COK work, norm rubrics and begin scoring | Continue collecting and scoring ICD and COK work  | Finish scoring ICD and COK work and write report |   | Present final ICD and COK report to IASC and IC for endorsement |